## Cover
Project Task Plan
Document history:
Version | Author | Data | Status | Description of change
V0.1 | Xiaolong Zhang | 2019-01-07 | Initial | Initial Version
V0.2 | Xiaolong Zhang | 2019-01-08 | Modify | Make Up Template
V0.3 | Xiaolong Zhang | 2019-03-14 | Modify | Modifies Pentest
V0.4 | Xiaolong Zhang | 2019-06-06 | Modify | Update 'Concept Phase' Descotiption and document
V0.4 | Xiaolong Zhang | 2019-06-10 | Modify | Optimise 'Concept Phase' Descotiption and document

## Cybersecurity Tasks
Market Information:
| Description | Responsible | Contact | Documents | Status | Deadline | Update Date | Review
Concept Phase
Feature Definition(Comparison) | Define the fcuntion, interaction and scopes of the feature |  |  | FeatureDefinition.docx
Cybersecurity Project Plan | Align cybersecurity with project plan and set up schedule for each phase |  |  | -
Threat Analysis and Risk Assessment | 1. Recognize security objects and data flow by DFDs of the system.DFDs foucs on the analysis of system feature. It has similar fucntion of feature definition. It will set up knowledeg of the interaction between system and outside actor and inner logical model. 2. Dectect threats and risks with threat tree Calculate threat level with EVITA and Identifying Cybersecurity Goals |  |  | DFDs.tm7 ThreatTree.vsd ThreatAnalysisRiskAnalysis.xlsx
Cybersecurity Concept | Security assumptions definition high-level Cybersecurity strategy for the feature |  |  | -
Functional Cybersecurity Requirements | Make up Cybersecurity requirements with upside items |  |  | CybersecurityRequirement.docx
Deviation Management | Manage the limitation for cybersecurity requirements |  |  | -
Initial Cybersecurity Assessment | Info
Analysis activities to identify requirements | Info
Desgin
Design Item
Technical cybersecurity requirements(F14)
Spec Matrix
Deviation Management
Implementation
Implementation Item
Deviation Management
Test
F14 Test Report
Fuzzing Test Plan
Fuzzing Test Report
Pen Test
Pentest Plan |  |  |  | Template of Pentest Plan.xlsx
Pentest Report Review
Production
Cybersecurity Sign Off